## Sheet1
Project Plan |  |  |  | Project Github link: https://github.com/chaumdh/project-1-submission | [5 empty] | milestone 1: component and page content added |  |  | milestone 2: complete either your components or your page |  |  |  | milestone 3: Finish Project & Test
# | Task | Person Responsibble | 2026-08-06 | 2026-08-07 | 2026-08-08 | 8/9/2026 - Lead checkin | 2026-08-10 | 2026-08-11 | 2026-08-12 | 2026-08-13 | 2026-08-14 | 2026-08-15 | 8/16/2026 - Lead checkin | 2026-08-17 | 2026-08-18 | 2026-08-19 | 2026-08-20 | 2026-08-21 | 8/22/2026 - Project due
| header - nav bar | Chau
| header - page tile image and title text | Everyone
| header - hamburger | Chau
| header - locations dropdown | Hector
| footer - 1 | Lederh
| footer -2 | Migo
| footer - 3 | Hector
| awards | Melany
remaining content of page (wiouth header, footer, or awards)
sign-in
| about | Melany
| adultprograms | Hector
| contact | Lederh
| home | Chau
| swimlessons | Migo
each page has css, js, html
hamburger
sticky nav bar
Notes
1 | Minimum 1 HTML table to display tabular data.
Featured a simple VUE component within the site.
| CSS reset |  |  | in pdfs
| sign-in has to open onto a modal |  |  | in pdfs
tests
how to push code into repo